## 273.7M
WELDING BREAK AT SPIRALING (GK PHASE 4 , SF11+12+13) - WELDING MACHINE BS13-11 (WSP18)
| Length | Weld Ref | Weld No | Series | Bobbin | Loading | Status | Remarks
3 | 282m | N-3 | 1 | 3 | 001 | L1B1 | On Bobbin | * Depends on sample N-2
2 | 210m | N-2 | 2 | 3 | 014 | L1B2 | On Bobbin | * Depends on sample N-1
1 | 149m | N-1 | 3 | 3 | 001 | L1B1 | On Bobbin | Tensile test result all passed - UTS 586.7 MPa (spec 530MPa) - Elongation 15% (spec 5%)
| 77.1m | N | 4 | 3 | 014 | L1B2 | Failed | * Welding break during spiraling at length 77.1m-Laying point
| 17.2m | N+1 | 5 | 3 | 001 | L1B1 | Lay On Pipe | * The weld has been laid on pipe * Distance between weld crack is 59.9m
8 | 637m | N+2 | 6 | 3 | 013 | L2B2 | On Bobbin | * Tensile test result all passed - UTS 636.6 MPa (spec 530MPa) - Elongation 14% (spec 5%)
6 | 506m | N+3 | 7 | 3 | 013 | L2B2 | On Bobbin | * Weld passed during laying * MPI before laying done and passed
7 | 575m | N+4 | 8 | 3 | 011 | L2B1 | On Bobbin | * Weld passed during laying * MPI before laying done and passed
4 | 374m | N+5 | 9 | 3 | 013 | L2B2 | On Bobbin | * Tensile test result all passed - UTS 619.8 MPa (spec 530MPa) - Elongation 12% (spec 5%)
5 | 457m | N+6 | 10 | 3 | 011 | L2B1 | On Bobbin | * Weld N+5 passed * No required to retrieve weld