## 940m
WELDING BREAK AT SPIRALING(BID 141KM SF 3X)-WELDING MACHINE BS13-11 (WSP18)
Length | Weld Ref | Weld No | Series | Bobbin | Loading | Status | Remarks
176.1 | N-7 | 01 | 07 | 009 | L1B1 | Not reachable
477.8 | N-6 | 02 | 07 | 003 | L1B2 | Not reachable
405.3 | N-5 | 03 | 07 | 003 | L1B2 | Not reachable
378.2 | N-4 | 04 | 07 | 003 | L1B2 | Not reachable
146.6 | N-3 | 05 | 07 | 003 | L1B2 | Not reachable
407.5 | N-2 | 06 | 07 | 009 | L1B1 | Not reachable
921.3 | N-1 | 07 | 07 | 013 | L2B2 | Not reachable
940 | N | 08 | 07 | 005 | L2B1 | Failed | -Welding break during spiraling at length 940m-Laying point -Replace weld 03-04 used Bs13-12 -MPI and visual passed
659.3 | N+1 | 09 | 07 | 013 | L2B2 | Not reachable
174.8 | N+2 | 10 | 07 | 005 | L2B1 | Not reachable
511.8 | N+3 | 11 | 07 | 005 | L2B1 | Not reachable
1459.1 | N+4 | 12 | 07 | 011 | L3B2 | Passed | -To be retrieve before laying-DONE at length 1459.1m -Replace weld 08-04 used Bs13-12 -MPI and visual passed -Tensile test passed : 563.3Mpa, 9% (530Mpa, 5%)
1226.1 | N+5 | 13 | 07 | 011 | L3B2 | Passed | -To be retrieve before laying-DONE at length 1226.1m -Replace weld 07-04 used Bs13-12 -MPI and visual passed -Tensile test passed : 586Mpa, 8% (530Mpa, 5%)
998.6 | N+6 | 14 | 07 | 011 | L3B2 | Passed | -To be retrieve before laying-DONE at length 998.6m -Replace weld 06-04 used Bs13-12 -MPI and visual passed -Tensile test passed : 579Mpa, 10% (530Mpa, 5%)
LEGEND:-
Welding passed
Weld sample to retrieve
Welding failed

## 841.8m
WELDING BREAK AT SPIRALING(BID 141KM SF 9X)-WELDING MACHINE BS13-11 (WSP18)
| Length | Weld Ref | Weld No | Series | Bobbin | Loading | Status | Remarks
| 310.8 | N-5 | 2 | 20 | 016 | L2B1 | Not reachable | * The weld has been laid on pipe * Distance between weld crack is 531m
| 303 | N-4 | 3 | 20 | 006 | L2B2 | Not reachable | * The weld has been laid on pipe * Distance between weld crack is 538.8m
| 92 | N-3 | 4 | 20 | 016 | L2B1 | Not reachable | * The weld has been laid on pipe * Distance between weld crack is 749.8m
| 83.5 | N-2 | 5 | 20 | 006 | L2B2 | Not reachable | * The weld has been laid on pipe * Distance between weld crack is 753.8m
1 | 848 | N-1 | 6 | 20 | 011 | L3B1 | On Bobbin | * To be rectrive done befofe laying * To perfrom tensile test
| 841.8 | N | 7 | 20 | 003 | L3B2 | Failed | * Welding break during spiraling at length 841.8m-Laying point
| 651.8 | N+1 | 8 | 20 | 011 | L3B1 | Not reachable | * The weld has been laid on pipe * Distance between weld crack is 190m
| 614.1 | N+2 | 9 | 20 | 003 | L3B2 | Not reachable | * The weld has been laid on pipe * Distance between weld crack is 227.7m
4 | 1375 | N+3 | 10 | 20 | 015 | L4B2 | On Bobbin | * To be rectrive done befofe laying * To perfrom tensile test
5 | 1413 | N+4 | 11 | 20 | 012 | L4B1 | On Bobbin | * Defend on result N+3
3 | 1218 | N+5 | 12 | 20 | 015 | L4B2 | On Bobbin | * To be rectrive done befofe laying * To perfrom tensile test
2 | 1184 | N+6 | 13 | 20 | 012 | L4B1 | On Bobbin | * To be rectrive done befofe laying * To perfrom tensile test
* Dummy